## Dashboard
Task ID | Task Name | Team | Task Owner | Start Date | Due Date | Task Duration | Status | Overdue? | Comments
T001 | Prepare Q4 Financial Report | Finance | Sarah Johnson | 2026-03-02 | 2026-04-20 | 49 | Completed | FALSE | Submitted to CFO for review.
T002 | Conduct Market Research | Strategy | Sarah Johnson | 2026-02-14 | 2026-02-23 | 9 | Completed | FALSE | Draft findings ready; awaiting survey data.
T003 | Redesign Website Homepage | Strategy | David Kim | 2026-04-10 | 2026-04-20 | 10 | In Progress | TRUE | Wireframes approved; development in progress.
T004 | Update Sales Forecast for FY2026 | Finance | Sarah Johnson | 2026-04-12 | 2026-04-30 | 18 | Completed | FALSE | Final version shared with Sales Director.
T005 | Implement CRM Upgrade | Strategy | James Miller | 2026-09-15 | 2026-10-10 | 25 | In Progress | FALSE | Vendor confirmed delivery timeline.
T006 | Plan Annual Company Retreat | HR | David Kim | 2026-09-18 | 2026-10-15 | 27 | In Progress | FALSE | Venue options being shortlisted.
T007 | Review Legal for Contracts | HR | Alex Chen | 2026-04-02 | 2026-04-15 | 13 | Not Started | TRUE | Updated contracts aligned with new regulation.
T008 | Launch Social Media Campaign | Marketing | Alex Chen | 2026-09-22 | 2026-10-12 | 20 | In Progress | FALSE | Initial creatives approved, campaign scheduled.
T009 | Recruit New Data Analyst | HR | Sarah Johnson | 2026-09-23 | 2026-10-20 | 27 | Completed | FALSE | First round of interviews completed.
T010 | Conduct Employee Survey | HR | Sarah Johnson | 2026-09-24 | 2026-10-05 | 11 | In Progress | FALSE | Survey questions finalized.
T011 | Prepare Investor Presentation | Finance | David Kim | 2026-09-25 | 2026-10-02 | 7 | Completed | FALSE | Draft slides ready; awaiting financial highlights.
T012 | Upgrade Infrastructure | Strategy | Sarah Johnson | 2026-09-26 | 2026-10-30 | 34 | Completed | FALSE | External consultant engagement pending.
T013 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2026-09-27 | 2026-10-07 | 10 | In Progress | FALSE | Three proposals shortlisted for management review.
T014 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2026-09-28 | 2026-10-18 | 20 | Completed | FALSE | Kick-off meeting scheduled next week.
T015 | Audit Internal Expense Reports | Finance | Emily Davis | 2026-09-29 | 2026-10-04 | 5 | Not Started | FALSE | Waiting for submission of all departmental reports.
Formulas:
Overdue? = AND(Table1[[#This Row],[Status]]<>"Completed",Table1[[#This Row],[Due Date]]<TODAY())
TASK MANAGEMENT TRACKER
Completed
7
2
Not Started
In progress
6
15
Total Tasks
2
Overdue Tasks

## Support Sheet
Status | Count | Owners | Count | Team | Count | Overdue
Completed | 7 | Sarah Johnson | 6 | Finance | 4 | 2
In Progress | 6 | David Kim | 3 | Strategy | 6
Not Started | 2 | James Miller | 1 | HR | 4
Total | 15 | Alex Chen | 2 | Marketing | 1
|  | Emily Davis | 3